## 25 May 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
| NTT | Sharag Goyal | Change & Transformation SME
|  | Vikram Bharwani | CTO Enterprise Architect
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
Mayuresh Mohan PARDESHI <mayuresh.mohan.pardeshi@hsbc.com>; Przemyslaw M GAWLAK <przemyslaw.m.gawlak@hsbc.com>; Megha4 AGARWAL <megha4.agarwal@hsbc.co.in>; Vikram BHARWANI <vikram.bharwani@hsbc.com>
| No. | Discussion Points
| 1 | Current setup has 4 different teams supporting Payments: Unix Team WAS Team MQ Team DB Team
| 2 | Pain Points: - working model and Jira Board setup for all team with well defined strucure - Auto Recovery - Know when something Breaks - Manual overhead for Database user creation, password reset, Access Restrictions. Need to be automated. - Self Healing Capabilities
| 3 | Key Pieces to work on by NTT: 1 - Agile Practices - Dashboards 2 - Integrate Automations for manual work 3 - Bring in tools to setup pipelines 4 - Infrastructure automation 5 - Automated Incident Management

## 01 June 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
| NTT | Sharang Goyal | Change & Transformation SME
|  | Vikram Bharwani | CTO Enterprise Architect
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
Mayuresh Mohan PARDESHI;Kate, Dattatray;Ash WALL;Przemyslaw M GAWLAK;Megha4 AGARWAL;Neeraj MALISETTY;Vikram BHARWANI;Goyal, Sharang;
| No. | Discussion Points | No. | Action Item
| 1 | Onboarding services: HSBC team have initiated a program to onboard Microsoft-based services before the arrival of the team. The approval was received yesterday from a cost perspective. This is to ensure that there is something to start working on when the team member lands. | 1 | Mayur will gather more information from Manish regarding the payment tracking system and size space implementation.
| 2 | Payment flow and Splunk integration: Mayur explained the key payment flow, starting from the AMH and going through various layers (Swift->Payment flow to AMH->Orchestration layer->Sanction screening-> Actual Payment System -> Gateway ). The services involved in this flow are being onboarded. Splunk integration for end-to-end payment integration via Splunk is already underway. | 2 | Mayur will share documentation of payment flows and touchpoints with the NTT team once available.
| 3 | Payment tracking system and observability: There was a discussion on the difference between a payment tracking system and moving into a size space. It was agreed to gather more information from Manish regarding this. As a starting point, the focus is on getting the logs consumed and understanding the frameworks for implementing observability. | 3 | The team will analyse the configuration of applications in Splunk and determine the work required for observability.
| 4 | Documentation of payment flows and touchpoints: The NTT team expressed the need for documentation on payment flows and touchpoints. Team would like to review existing documentation, if available, to gain insights into the applications and touchpoints involved. This information will help analyse the configuration in Splunk and plan for observability and integrity checkpoints | 4 | Collaboration with the architect community will be initiated to gather their inputs on monitoring tools and strategies.
| 5 | Configuration of applications in Splunk: It was mentioned that only 15 to 20% of applications are currently configured in Splunk. The NTT team wants to identify the applications that are already configured and those that are not. This will help in understanding the current state and determining the work required to achieve the desired state. | 5 | NTT team will gather information on DevOps tools and their use in the HSBC, including version control, automation, deployment management, and communication.
| 6 | Utilizing previous knowledge and experience: The team discussed leveraging their knowledge and experience from previous projects, including their work at HSBC and WPP. Team emphasized the importance of understanding the existing architecture and monitoring tools deployed. Collaboration with the architect community was proposed to gather inputs and formulate a unified strategy. | 6 | Mayur will provide an overview of the infrastructure setup, particularly focusing on team support and database deployment practices.
| 7 | DevOps tools and automation: The NTT team highlighted the need to understand the DevOps tools used within the organization. They mentioned tools like GitHub, Bitbucket, Jenkins, CircleCI, GoCD, and others. The goal is to identify the primary tools used for version control, DevOps automation, deployment management, and communication
| 8 | Infrastructure setup: The NTT team expressed interest in understanding the current infrastructure setup across applications. Mentioned the importance of achieving high availability and zero downtime for cloud networks. Team also highlighted the need to improve deployment practices for databases.

## 12 June 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
| NTT | Sharang Goyal | Change & Transformation SME
|  | Vikram Bharwani | CTO Enterprise Architect
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
Mayuresh Mohan PARDESHI;Kate, Dattatray;Ash WALL;Przemyslaw M GAWLAK;Megha4 AGARWAL;Neeraj MALISETTY; Goyal, Sharang; Sohit Pruthi; Rohit Prakash Kherde
No. | Discussion Points |  |  | No. | Action Item
1 | The meeting started with a discussion on potential issues found in the reportings and collaboration with vendors. The issue was identified and reproduced in the vendors' environment, emphasizing the importance of thorough testing for the Tier 0 application. |  |  | 1 | NA
2 | HSBC pointed out exhaustive testing is necessary due to the critical nature of the payments application. The testing would continue for the rest of the week until the application went live. Additionally, monitoring and watch over the application would be conducted in the following week. |  |  | 2 | NA
3 | The discussion then shifted to incident management, data cleansing, severity, and priority. The need for accurate data and current state analysis was emphasized, and it was decided that data cleansing would be avoided initially to maintain the current state. Further discussions with problem management and Richard Clark were planned to clarify definitions and processes. |  |  | 4 | HSBC to share volumetrics and plan a followup discussion with Richard Clark who is looking into Problem Management
4 | Assigning individuals to work on build management and deployment management was proposed. The focus would be on Tier 0 applications, with the understanding that other tiers would follow suit. The need for clear documentation and tracking of responsibilities within the team was highlighted. |  |  | 5 | HSBC to create a JIRA Board and assign task for this assignment accordingly to track & monitor daily progress
5 | The NTT team expressed the need for clear definitions and understanding of application tiers and monitoring practices. It was agreed that obtaining detailed definitions from HSBC would be essential, along with a breakdown of services by tiers and the availability of monitoring tools like Splunk. |  |  | 6 | NA
6 | The scope of services for Tier 0, 1, and 2 applications was briefly discussed. Tier 0 applications were identified as critical and essential to the functioning of the bank, while Tier 1 applications were important but not as critical. Tier 2 applications were considered less critical, and an official definition of these tiers would be obtained from HSBC |  |  | 7 | HSBC to share tier wise application details with NTT Team
7 | The availability of monitoring tools and automation for different tiers was confirmed, and the possibility of obtaining a clear overview of applications and associated tools was discussed. The need to analyze critical payment flows and methods within the framework was recognized, and it was agreed that relevant data would be provided. It was also mentioned that Tier 0 Applications are fully automated |  |  | 8 | HSBC to share build, release, monitoring and other automation tools being used per application (along all the tiers) with NTT Team
9 | The framework for monitoring and alerting was briefly explained, covering hardware monitoring, application monitoring, health rule setting, and alert filtering. It was acknowledged that further enhancements and refinements to the framework might be necessary. HSBC is looking at following from monitoring aspects: 1) Hardware Monitoring - know about CPU, Memory Consumptions etc. 2) Application Monitoring - applications logs to be monitored for failures and alerts 3) Health Dashboards - application dashboards should be there to showcase health of apps |  |  | 9 | NTT Team to work on monitoring aspects in lines with the aforesaid envisions and plan accordingly (No action until deep dive sessions are arranged)
10 | It was noted that the previous monitoring framework had been effective when it was actively implemented, but due to shifting priorities, its adoption had declined. The importance of reestablishing the observability piece and ensuring consistent monitoring practices was highlighted. |  |  | 10 | NA
11 | The availability of details on payment flows and methods was acknowledged, although it was mentioned that updates and changes might require reevaluation. HSBC is using CHAPS as Payment System which is a Tier 0 Application. |  |  | 11 | NA
12 | HSBC has future plan to move towards a Hybrid Cloud, engineering their practice in a certain way that Applications with confidential data would stay in Private Cloud and other applications will move to Public Cloud thereby maintaing securities and data governance. Currently all HSBC Applications are available in Private Cloud (using Kubernetes) |  |  | 12 | NA
13 | NTT shared initial draft version of Workshop plan along with the stakeholders required to be present during the discussion. It was further discussed that an updated version of this document will be shared with HSBC in order to provide more clarity on who to bring for the workshops and arrange sessions accordingly. |  |  | 13 | NTT Team to share the updated Workshop planning document with HSBC including Stakeholders required for each of the session

## 13 July 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
Przemyslaw Gawlak
Ash Wall
Neeraj Malisetty
| NTT | Sharang Goyal | Change & Transformation SME
|  | Dattatray Kate | PM & Scum Master
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
No. | Discussion Points |  |  | No. | Action Item
1 | Required overview session and list of stakeholder |  |  | 1 | 1. NTT to share required overview sessions and stakeholder list for the sessions 2. Overview session will be planned on 18th, 20th, 25th and 27th July
2 | Project Plan |  |  | 2 | NTT team to create tentative project plan and share with Mayuresh

## 18 July 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
Przemyslaw Gawlak
Ash Wall
Neeraj Malisetty
| NTT | Sharang Goyal | Change & Transformation SME
|  | Dattatray Kate | PM & Scum Master
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
No. | Discussion Points |  |  | No. | Action Item
1 | Laptop allocation and Access to HSBC tools |  |  | 1 | 1. Laptop request approved. Megha will work on access to HSBC tools for NTT Data team 2. Megha will create confluence page which contain details of access and tools require for the assignment 3. Sohit to share list of access which may be required
2 | Overview session |  |  | 2 | 1. Mayuresh will share details of stakeholders and their availability for the overview sessions
3 | Mayuresh travel date to india and workshop plan |  |  | 3 | 1. Mayuresh will be in India from 7th Aug to 11th Aug for Workhop. (Tentative)
4 | Project Plan |  |  | 4 | NTT to share weekly by week plan frm 26th July

## 20 July 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
Przemyslaw Gawlak
Ash Wall
| NTT | Sharang Goyal | Change & Transformation SME
|  | Dattatray Kate | PM & Scum Master
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
No. | Discussion Points
1 | NTT Data team will send invite for overview sessions
2 | Mayu will provide confluence page space admin access to NTT Data team
3 | NTT Data team to plan project kick off meeting with Manish on 28th July
4 | A kick off meeting walkthrough with Mayu will be on 26th July
5 | Megha will setup Jira board for the project.
6 | Datta will schedule daily standup meeting from 27th July.

## 25 July 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
Przemyslaw Gawlak
Ash Wall
| NTT | Sharang Goyal | Change & Transformation SME
|  | Dattatray Kate | PM & Scum Master
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
| No. | Discussion Points
Major Markets: UK, USA and Hong Kong
SAG – Swift Alliance Gateway
AMH – Alliance Message Hub (has a SAPI on top of it, have 4 queues into SAG)
POL – Payment Orchestration Layer
GPE – Global Payment Engine (Finastra Product)
GMG – Group Message Gateway
PDP – Payment Data Platform (on GCP Cloud)
PDL – Payment Data Lake (Datawarehouse)
GPS to Datawarehouse happens via an EOD Batch File
Inbound Transaction Flow: SAG > AMH > POL > GMG > GPS > Datawarehouse
Outbound Transaction Flow: GPS > GMG > POL > AMH > SAG
All Tier 1 Application have Monitoring and Alerting setup à using Splunk, AppD and Patrol based monitoring.
Incidents Severity -> High, Medium and Low
Warning -> no alert is created.
Problem Management
Change Management
Incident Management
Two Data Center – Wakefield and South Wakefield
Data Guard for Apps with availability 4 9s (99.9999%)
Golden Gate for Apps with availability 5 9s (99.99999%)
Deployment Tool Used: RTC
Pending Question: How are repositories defined among Apps? GIT

## 27 July 2023
Attendees | HSBC | Mayuresh | Automation Lead
|  | Megha | Automation Team Member
Przemyslaw Gawlak
Ash Wall
| NTT | Sharang Goyal | Change & Transformation SME
|  | Dattatray Kate | PM & Scum Master
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
|  | No. | Discussion Points
|  | 1 | Confluence admin space access to Sohit, Rohit and Sharang
|  | 2 | Catch up call to be scheduled by Sohit
|  | 3 | Pending overview session to be planned by Sohit
|  | 4 | Rohit and Sohit will review initial pre onboarding question replies from HSBC

## 01 August 2023
Attendees | HSBC
|  | Megha | Automation Team Member
Przemyslaw Gawlak
Ash Wall
| NTT | Sharang Goyal | Change & Transformation SME
|  | Dattatray Kate | PM & Scum Master
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
|  | No. | Discussion Points
|  | 1 | Discussion on the access of splunk,appdynamic,xmatter, grafana, SNOW and other requested access by NTT team
|  | 2 | Access for Jira/Confluence,QlickView,Appdynamic,Jenkins,SNOW, graffana are provided
|  | 3 | For the remaining Megha is going to check with the application team.
|  | 4 | Update on initial on-boarding question for which ticket has already been raised in Jira board, Ash, Megha, Przemyslaw Gawlak will update the same.
|  | 5 | Gawlak will forward invitation of Splunk on-boarding to NTT team
|  | 6 | Sohit will setup call with Ash and Rohit for discussion on payment application, tier wise distribution and will also try to cover volume metric with respect to each flow

## 03 Agust 2023
Attendees | HSBC | Mayuresh
|  | Megha | Automation Team Member
Ash Wall
| NTT | Sharang Goyal | Change & Transformation SME
|  | Sohit Pruthi | Automation Architect
|  | Rohit Kherde | Payment SME
|  | No. | Discussion Points | Action Items
|  | 1 | NTT team was looking from perspective of getting tier wise distribution, region wise distribution of application and volume metric
|  | 2 | The incident data can be found from service performance dashboard by selecting incident summary and then filtering > Export into excel and then apply filter on owning org WSIT, WSIT GPS, WSIT GPS prorcessing those are belong to wholesale payment group and should be check to get the incident.
|  | 3 | On Cummilative platform there is service,which required synch between all the nodes and service got fail leading to big incident,as the it affect the whole payment system to stop working for 4hr.
|  | 4 | Need to ask incident and alert data for month of June from Manoj and need to match it with the incident report from service now. - Action item | 1
|  | 5 | There is assumption that this 8 incident are created only by service providers as incident created in service test are low in number, need to find the gap between alert and incindent. - Action Item | 2
|  | 6 | Meeting with Richard on 8th August and he can help us in understandig incident. - Action Item | 3
|  | 7 | NTT team will meet manoj to discuss on this incident thing - Action item | 4
|  | 8 | Datta Doke he was part of CTP before and can help us in getting good insight - Action item | 5
|  | 9 | Ash has done research from his side for finding volume, value of different payment flow but unable to find, according to him its not published in confluence.
|  | 10 | There is service inventory which have details of application and tier wise distribution anything which are tier 0 those are to be targeted.
|  | 11 | NTT team will not look into importance of application will just consider all the application which falls under tier 0,1,2 and will work on them.
|  | 12 | HSBC team do the performance test of all tier 0 application regularly and as a part of performance they look at are there any changes in volume and not the values, volume metric
|  | 13 | There was a situation or incident where performance has been done based on assumption that due deligence is correct, without actually looking at from where they get the numbers and then incident happened and now team are changing there own performance process and now started collecting evidences, volume which Spruha give will be enough.
|  | 14 | Setting tier for application is different process which will not analyze, NTT data team will by tier which is already setup - Action item | 6
|  | 15 | Infrastructure inventory, there is a spreadsheet which has all detail of all the service, servers, tier, application name, severs role kind of CMDB list. Mayuresh will share this CMDB list, the dumb - Action item. | 7
|  | 16 | Automation Roadmap or backlog which team already and to provide sources.
|  | 17 | Overview ot team structure pending from mayuresh will happen this week sohit will send invitation. - Action Item | 8
|  | 18 | Automation backlog meeting,morning megha will setup - Action item | 9

## 10 August 2023
HSBC | Mayuresh
Megha
Ash Wall
Przemyslaw Gawlak
Abhishek Kumar
NTT | Sharang Goyal | Change & Transformation SME
| Sohit Pruthi | Automation Architect
| Rohit Kherde | Payment SME
| Dattatray Kate | PM & Scum Master
| No. | Discussion Points | Action Items
| 1 | NTT team has shared thought of Creating Dashboard in splunk which will be user driven, people might actually creating lot of dashboard without relievance. The team would need further details on what exactly are the stages and how we can start guiding on this approach.Also the area where NTT team has already worked is in extension within Splunk like DB connect , SmartData, how indexing and quering splunk can work in order to get better result need furhter dicussion around the Splunk | Roadmap
| 2 | In term of How Splunk is setup HSBC team can share the design document to reiview they are not concret as they are changing, unless there are any obvious issue which they have already seen and need to tackle that. HSBC team to share design document. How to setup role, how to setup indexes and provide best practises of Splunk. Gawlak was a Splunk administrator for many year | Action item
| 3 | Ananta and Veeraju are the Splunk owner, they are POC also look at the service
| 4 | For the Licensing part there are different part initially Automation team owned the license part they procure the license and hands it over to the Ananta team by importing license into there service, purchase on behalf of the team and they will manage the License. Licenses are procure directly from the Splunk. It got in cheap cost in a discounted price
| 5 | Stephen K is the infrastructrure architech for the enitre payment not into splunk, His role involved looking into new service that is coming in and what server that should be going on, like if it should use ITB or VM, how the design will be. He understand design of HSBC also knows how many VM, capacity
| 6 | When are the application team will get involed into this? Once we have date Premiz is creating the plan and which application to be board on what time and once done they will be working with individual application owner to make this installation possible
| 7 | Mayuresh team will create automation then they will give guidelines to ITSO to install Splunk. And that's why they are creating flow chart showing step wise instruction.
| 8 | Before starting the process, automation teams needs to understand how much will be the data to pump in,they have done some work with respect to that, also details and estimation are shared with CEO and base on that service owner has been informed about the pricing and all.
| 9 | Splunk License, Splunk hardware and FTE, FTE was about 100 thousand License cost was about 200-300 thousand and hardware was 700 thousand for AP and EU instant that will suffies for data requirment as we know today
| 10 | NTT team had a session with Chetan from WOLF, Gurdit from Change management
| 11 | NTT team has shared day wise plan for next week
| 12 | NTT team has decided to go with 3 application GPE,WOLF, POL from incident management perspective. Base on this roadmap will be created
| 13 | Currently eveything is configured in Patrol, alerts has been decided by development team and not by PE team. There are inconsistency around how severity and how priority around these alert.How alert are raised, how incident are raised and how they are managed further in life cycle there are inconsitent approaches. NTT team are analyzing all this data as and when provided and will share recommendation around the same by next few weeks | Roadmap/Action item
| 14 | NTT team is currently working on understanding incident management, team structure , patrol tool setup, how alerts are generated and monitored

## 17 August 2023
HSBC | Mayuresh
Megha
Ash Wall
Przemyslaw Gawlak
Abhishek Kumar
NTT | Sharang Goyal | Change & Transformation SME
| Sohit Pruthi | Automation Architect
| Rohit Kherde | Payment SME
| No. | Discussion Points | Action Items
| 1 | NTT team discussed about the things they are looking for like how the application are manager, how incident are configured, understanding tools. How they manage incident in terms of alerts, and also team wise structure process. Second is aspect is around development team CI/CD pipeline and aslo shared the current status with respect to WOLF and GPE. Discussion also happened around the time of stakeholder. Team need help for GPE dev side.
| 2 | POL PE can Saint Y S Liu, he supports POL in production, knows about incident, alerts. Knows technically how things work, also supporting POL production, also working on automating thing can be good for incident and automation
| 3 | HSBC team wants to add Splunk as a part of assignment. There is weekly meeting of splunk, HSBC team forwarded the meeting invitation for Splunk implementation
| 4 | NTT team suggested best practises around implementation of Splunk.
| 5 | HSBC and NTT team decided to have a call on the splunk implementation for building the blocks and foundation.NTT team will take lead to setup the meeting with HSBC team and NTT team for the splunk structure define
| 6 | As of now there is no format in Splunk what are the alert key word on which index are to be done and not yet decided.
| 7 | Splunk implementation is first phase, second phase is what is important to get alert on and define the application is green or red or amber, What are the matrix which are absoultelu important from business perspective and technical point once are all defined then we can start designing the application and to get this achieve what we need to do and this may be not one tool, may be need to check on splunk and also on AppDynamic. Combination of both can show certain conditions about status green, amber or red color defining category this will be the second phase where we would define how do we define application, third phase is implementation of same where logs patterns will get change, change the transaction on Appdynamic or other thing to get on the point. Get the framework there with enough detail to get HSBC team to get it implemented | RoadMap
| 8 | To get the name of key API which are relate to payment flow is difficult to get as there are no documentation in one single place

## 22 August 2023
HSBC | Mayuresh
Megha
Ash Wall
Przemyslaw Gawlak
Abhishek Kumar
NTT | Sharang Goyal | Change & Transformation SME
| Sohit Pruthi | Automation Architect
| Rohit Kherde | Payment SME
| No. | Discussion Points | Action Items
| 1 | NTT team has shared update on current state. Team is observing the current system of 3 application. Team also share about automation backlog analysis, IE and PE automation which will be added in roadmap as well.
| 2 | Team also share about the area laging behind which are POL and GPE due to unavalibilty of stakeholder. but meeting has been schedule for this week with GPE deveoplment team and POL devops team. Got some information from Ashish about POL system but detail call will be in this week. WOLF end to end understanding.
| 3 | As per HSBC right now there is no organized approach with respect to automation of different application, rather they are engaging with PE team working on individual ticket created in Jira. | RoadMap
| 4 | From monitoring perspective to understand current flow if any analysis is done? - HSBC team has done some analysis of same, outcome of which is to put every application on AppDynamics and reduce dependency on other application like Patrol and other tools. They analyzed all Tier 0 services some 1 and half year before.HSBC team to share confluence page with respect to that analysis
| 5 | HSBC team want to have a framework or number of question if this something happened how to categorize if application is amber, green, red. What are the key metrics you look at to define this? Do you look at business transaction? Do you look at hardware or combination of both action and traffic? how do you categorize if application is healthy? Once we have defined answer then we can come up with technical requirement. example: You want loging page as fast as to be possible, what does the AFAP means, is it mean less than 5 second. Comes with such requirement and then transfer it either to AppDynamic and Splunk. By end of november the questionare should be ready to show to Munish and also test drive of the services | RoadMap
| 6 | There is no transaction tracing currently, teams know how the payments flow from one service to another that can provide. There are more of how rules are dump. HSBC team also shown the POL micro-services. Only POL is micro service base, while the WOLF is not on micro-service its still running on VM with WAS server.
| 7 | Start with basic information we have for wherever we don’t have microservices base architecture, we can start with critical touhpoint and then develop it with over the time. So | RoadMap
| 8 | When we are onboarding splunk on an application for WOLF or GPE, how are the team is going to identify what are the alerts to be setups on what are key words for indexing? Answer - Those are secondary requirement or second phase for HSBC team, currently all they need to do is get the application log onboarded on the splunk. First step is to get application log. to have the fund for the next year Second phase is looking at the relevenace of the log do we have enough log to make sense of information or we want to change the log and how to do transaction streching is there reference point or is the log and how we do transaction streching for cross application? is there a reference point to anchor it Third phase - Create SRE model | RoadMap
| 9 | There are 2 approach for implementation of Splunk either have application index created on splunk and slow down onboarding process of application or adoption which mean in next year we were funded differntly and we don’t have fund and the second approach is to onboard all the application as early as possible and then funding question will not be there and we can focus on maturing the loggin system | RoadMap
| 10 | Getting the application on the Splunk is the first phase and current defination.HSBC team have a plan in place which show milestone and stages
| 11 | DataDog is not is use today its only AppDynamic, patrol and splunk is way forward and AppDynamic. From the sense of micro-service which will be better will be suggested by NTT team and same will be shared with other. | RoadMap
| 12 | From Prometheus shipping data into splunk and then setting up alerts on Splunk setup of POL and should go away when splunk is on-boarded. For IKP base application how show | RoadMap

## 24 August 2023
HSBC | Mayuresh
Megha
Ash Wall
Przemyslaw Gawlak
Abhishek Kumar
NTT | Sharang Goyal | Change & Transformation SME
| Sohit Pruthi | Automation Architect
| Rohit Kherde | Payment SME
| No. | Discussion Points | Action Items
| 1 | POL is a micro-service base application it has got probable 300+ pods running for different things.POL is a central unit of cordinating all of payment services. New technology there is always incident happened around. If POL is down whole proecss is down. In term of monitoring POL is sligtly off. POL is setup on IKP. 8 nodes 8 VM, kubarnative cluster around it and dedicated to payment team. SAPI is also on IKP. There is a namespaces in it and they have got SAPI, RTP. POL consume 90% of the resources.Anything which is on IKP is on Splunk. Currently POL is on splunk. GPE is not on the Splunk but SAPI layer is on the splunk
| 2 | There are various stakeholder in IKP, central team no control by automation team, cannot access node they maintain the cluster and automation team looks after namespace. CTB team and DevOps team, Production engineering team they take care of namespace form monitoring, deployment
| 3 | In term of monitoring, IKP teams they have got Datadog license product. Automation team do not have access of it. They use dataDog look at the namespaces and utilization by cluster in the way they want to maintain all there nodes in the healthy state, so they keep track on uses like how much they are utilitzing, under utilizing, over utilitizng, any problem around that. Also if board is constantly restarting and it could be due hardware, network. They also google anthos as a layer for kubernative. ATeam do not have control or visibility on it, IKP team have they do via DataDog and Splunk.
| 4 | IKP team use different Splunk then the one Automation team use, it is decdicated to IKP team it is for capacity management. Use to monitor Nodes, anthos, they have access of logs and backend. Platform is stable enough, AT team raise the case and hands it to IKP team
| 5 | Application as monitroing for payments, pods, deployment,logs are genereated and then pump into splunk, there they got alerting setup and everything around dashboard.
| 6 | People started creating many dashboard on Splunk was slowing down splunk the service provider to the point where they have to restrict them not to do real time searches. They keep running on the background making it slow. | RoadMap
| 7 | We are doing monitoring likes application level monitoring such as response time, loggin, error,kind of error, services down, out of memory, readiness issue, capacity issue. | RoadMap
| 8 | Need to define dashboard in a control way, defining. There is no defination yet we need to define the metric what will be called green,red, amber. | RoadMap
| 9 | Garbage dump or collection are not send directly by the pod to the splunk it goes via prometheus> Jmack exporter > splunk. The amount of matrix generate is massive to the point that splunk get slow down.
| 10 | Teams expect to have data within 15 to 20 second but due to Jmack exporter getting slow, they started loosing data at a time in productio or real time when they run performances as it start loading so much data. | RoadMap
| 11 | Now in the production they are using Jmax matrix cut short the amount things to be monitor tovery minimum, which is not a idle solution and the reason can be because of Jmack exporter, prometheus. Also why there is issue with capcacity or the issue with respect to funds but also long term solution like be in position to have more IKP resources for the specific application on boarder, adding new services to the existing structure will add more problem that is why they started looking at AppDynamic | RoadMap
| 12 | The problem with the splunk is we cannot se flowmap. We cannot see which services called which services, how the transaction are hopping from one service to another in the open source application so we don’t have formal support for them and there is no one to call.
| 13 | HSBC need someone as point of contact for application in case the issue aris, whom they can call and get it fix away rather than small workshop. | RoadMap
| 14 | Getting the matrix updated and not having the flowmap visibility and undertstanding of who the garbage dump is done for each of the services. Two different matrix not currently in line causes problem and that's why they look at AppDynamic or some other application. AppDynamic will will be use for infra monitoring | RoadMap
| 15 | Currently they are using other way around like outputing the data way collection into log which they are shipping into splunk to get information but not able to get more details like CPU utilization or hardware details | RoadMap
| 16 | Map of services like which services are talking to which services so that payment can be track between this services like 101 or 103. And also which services are slowing down. And AppDynamic does automated baselining and base on that if it see any problem it calls out.Wether we can also get CPU related matrix, hardware matrix showing clear picture of what causing the problem. Customize the flowmap | RoadMap
| 17 | HSBC team are trying to have a flowmap of the payment flow on AppDynamic for CHAPS inboud and outbound payment flow. Flow map within POL | RoadMap
| 18 | Why only AppDynamic why not other free source? What AppDynamic does is it linked up to the partner system as well. From the application monitoring perspective this is very important and not from transaction perspetive. Helps to undertstand how the application are connected to each other .
| 19 | Grafana do not have a proper way of monitoring kafka, there are also so many issue with Kafka. All we use grafana is for cords monitoring not for application but CPU and hardware, namespace place that does not goes into splunk but in Jmax exporter. Grafana comes into picture only when there is prometheus.
| 20 | There is overlap between whats there is splunk and grafana, with Kafka there is many thing come from log.

## 29 August 2023
HSBC
Megha
Ash Wall
Przemyslaw Gawlak
Abhishek Kumar
NTT
| Sohit Pruthi | Automation Architect
| Rohit Kherde | Payment SME
| No. | Discussion Points | Action Items
| 1 | NTT team has shared update on current state. Team also share about automation backlog analysis,WOLF, POL and GPE finding current analysis
| 2 | NTT team has also shared the risk and issue they are facing getting in hand on POL stakeholder to have detail dicussion
| 3 | HBSC team suggested name of POL contact person from PE team Atul Mangam. Also team dicussed about new joiner Rahul Shinde who is head of APAC to have meeting with same

## 31 August 2023
HSBC
Megha Agarwal
Ash Wall
Przemyslaw Gawlak
Abhishek Kumar
NTT | Sharang Goyal | Change & Transformation SME
| Sohit Pruthi | Automation Architect
| Rohit Kherde | Payment SME
| No. | Discussion Points | Action Items
| 1 | NTT team has shared update on current state. Team also share current analysis,WOLF, POL and GPE update
| 2 | NTT team has a meeting schedule for tomorrow 1st september with Atul to discuss about POL PE process
| 3 | NTT team has found out that there is no conistent in the onboarding manual and the process while dicussing about mail thing
| 4 | Team also had a dicussion around AppDynamic and Splunk implementation around different application. It uses and how much it has been utilized
| 5 | With help of HSBC team, NTT team was able to see the AppDynamic dashboard created for WOLF and other application